## Sheet1
Activity | Estimated Effort in Days | Notes
Scope/ Content Analysis | 0.5 | Review the legacy WordPress site and GitHub Pages site to identify features, pages, and integrations to be validated. | Total Estimated Effort = ~10 Person-Days (≈ 2 weeks full-time)
Test Planning & Documentation | 1 | Test Plan, review, final sign-off.
Test Case Design & Test Data Preparation | 2 | Test scenarios for functional, content verification, and UX; prepare sample data (RSVP, external links).
Environment Setup/ Build Verification | 0.5 | Local Jekyll setup, GitHub Pages build validation.
Sanity Testing | 0.5 | Quick validation of core flows.
Functional, Content & UI/UX Testing | 1 | All pages, navigation, Slack/Guild/social redirects, responsive layouts, theme switching,
Performance Testing | 1 | Page load, caching, responsiveness checks.
Accessibility Testing | 0.5 | WCAG checks.
Security & Compatibility Testing | 0.5 | Browsers (Chrome, Edge, Firefox), devices (desktop, tablet, mobile).
Regression Testing (post-fixes) | 1 | After bug fixes and re-deployments.
Stage/Production Sanity Validation | 0.5 | Smoke test on staging, final validation on prod.
Defect Management & Reporting | 0.5 | Logging in Issues, daily/weekly reporting.
Test Closure & Lessons Learned | 0.5 | Final summary report, retrospection.
Total | 10