## Summary
Project Name: |  | CivicTechTo Website Migration
Test Designed & Executed by: |  | Swapnajit Mohanty
Iteration/Cycle: |  | Sprint 1
Date:
Test Execution Summary
Total Test Cases | Passed | Failed | On Hold | Blocked | N/A
72 | 52 | 3 | 9 | 7 | 1
Highlights:
1. Migration is partially validated due to archive data files are present but not rendered in UI.
2. Core UI/Navigation tested successfully.
3. 9 functional test cases remain on hold until the required content or records are populated.
4. 7 test cases are blocked due to missing prerequisite content and local limitations
5. Retesting of pending scenarios to be conducted on prod/staging environment before sign-off.
Summary by Testing Type | [6 empty] | Summary by Priority
Type | Total | Passed | Failed | On Hold | Blocked | N/A | Priority | Total | Passed | Failed | On Hold | Blocked | N/A
Migration | 6 | 5 | 1 | 0 | 0 | 0 | Critical | 22 | 14 | 2 | 2 | 3 | 1
Functional | 25 | 12 | 0 | 9 | 4 | 0 | High | 39 | 31 | 1 | 5 | 2 | 0
Integration | 15 | 13 | 0 | 0 | 2 | 0 | Medium | 10 | 6 | 0 | 2 | 2 | 0
UI/UX | 3 | 2 | 1 | 0 | 0 | 0 | Low | 1 | 1 | 0 | 0 | 0 | 0
Performance | 8 | 8 | 0 | 0 | 0 | 0 | Total | 72 | 52 | 3 | 9 | 7 | 1
Accessibility | 9 | 8 | 1 | 0 | 0 | 0
Security | 3 | 1 | 0 | 0 | 1 | 1
Compatibility | 3 | 3 | 0 | 0 | 0 | 0
Total | 72 | 52 | 3 | 9 | 7 | 1

## Execution
Test Case ID | Type | Test Title | Pre-Conditions | Test Steps | Expected Results | Priority | Actual Result | Status | Remarks/ Test Data
TC-CivicTech-001 | Functional | Verify homepage loads successfully | Server is running locally | Open http://localhost:4000 | Homepage should load without errors and display CivicTech Toronto header, contents, and navigation menus | Critical | Homepage is loaded successfully without errors. Contents/headers/menus are displayed correctly | Pass | This test requires a content comparison with the old site.
TC-CivicTech-002 | Functional | Verify top navigation menu items | Homepage loaded | 1. Click on Menu dropdown 2. Check options available | Following options should be available - About Us Get Involved Code of Conduct Hacknights Projects Resource | Critical | All reuired options are available | Pass
TC-CivicTech-003 | Functional | Verify “About Us” page navigation and content | Homepage loaded | 1. Click on Menu dropdown 2. Click on About Us | User should be navigated to About Us page. Page content should be displayed correctly and match with title | Critical | User navigates to the desired page. Content matches with title and old site. | Pass | This test requires a content comparison with the old site.
TC-CivicTech-004 | Functional | Verify "Read our Code of Conduct" link on About Us page | Homepage loaded | 1. Click on Menu dropdown 2. Click on About Us 3. Scroll down and click on "Read our Code of Conduct" | User should be navigated to Code of Conduct page. Page content should be displayed correctly and match with title | High | User navigates to the desired page. Content matches with title and old site. | Pass | This test requires a content comparison with the old site.
TC-CivicTech-005 | Functional | Verify "See all past speakers" link on About Us page | Homepage loaded | 1. Click on Menu dropdown 2. Click on About Us 3. Scroll down to Past Speakers section 4. Click on "See all past speakers here" 5. Check profiles | User should be navigated to People page. List of speakers should load correctly | High | User navigates to People page. However, no speakers or people are available | On Hold | This test requires a content comparison with the old site. Execution - Data population is not available in the current _data folder. Related historical records exist only in the /archives directory (e.g., _projects, _people). Test case placed on hold until migration data is connected to UI.”
TC-CivicTech-006 | Functional | Verify the links under "Our Supporters" | Homepage loaded | 1. Click on Menu dropdown 2. Click on About Us 3. Scroll down to Our Supporters section 4. Click on each link (Visit The Toronto Star website, Visit Open Data Team website) | Each link should navigates to the correct page without errors. Page content should be displayed correctly and match with title | Medium | No Links available under Our Supporters (Known issue) | Blocked | Data population is not available in the current _data folder. Related historical records exist only in the /archives directory (e.g., _projects, _people). This test case can be exceuted only after migration data is connected to UI.”
TC-CivicTech-007 | Functional | Verify “Get Involved” page navigation and content | Homepage loaded | 1. Click on Menu dropdown 2. Click on Get Involved | User should be navigated to Get Involved page. Page content should be displayed correctly and match with title | High | User navigates to the desired page. Content matches with title and old site. | Pass | This test requires a content comparison with the old site.
TC-CivicTech-008 | Functional | Verify “Code of Conduct” page navigation and content | Homepage loaded | 1. Click on Menu dropdown 2. Click on Code of Conduct | User should be navigated to Code of Conduct page. Page content should be displayed correctly and match with title | High | User navigates to the desired page. Content matches with title and old site. | Pass | This test requires a content comparison with the old site.
TC-CivicTech-009 | Functional | Verify "Hacknights" page navigation and content | Homepage loaded | 1. Click on Menu dropdown 2. Click on Hacknights | User should be navigated to Hacknights page. Page content should be displayed correctly and match with title | High | User navigates to the desired page. However, no records available | On Hold | Data population is not available in the current _data folder. Related historical records exist only in the /archives directory (e.g., _projects, _people). Test case placed on hold until migration data is connected to UI.”
TC-CivicTech-010 | Functional | Verify "Projects" page navigation and content | Homepage loaded | 1. Click on Menu dropdown 2. Click on Projects | User should be navigated to Projects page. Page content should be displayed correctly and match with title | High | User navigates to the desired page. However, no records available | On Hold | Data population is not available in the current _data folder. Related historical records exist only in the /archives directory (e.g., _projects, _people). Test case placed on hold until migration data is connected to UI.”
TC-CivicTech-011 | Functional | Verify "Resources" page navigation and content | Homepage loaded | 1. Click on Menu dropdown 2. Click on Resources | User should be navigated to Resources page. Page content should be displayed correctly and match with title | Medium | User navigates to the desired page. However, no records available | On Hold | Data population is not available in the current _data folder. Related historical records exist only in the /archives directory (e.g., _projects, _people). Test case placed on hold until migration data is connected to UI.”
TC-CivicTech-012 | Functional | Verify that event details are displayed under "Events" section | Homepage loaded | 1. Scroll down to "Events" section 2. Check content | Events section should display list of past/upcoming events with correct formatting Registration link should be available for upcoming events. | Critical | No records are available | On Hold | Data population is not available in the current _data folder. Related historical records exist only in the /archives directory (e.g., _projects, _people). Test case placed on hold until migration data is connected to UI.”
TC-CivicTech-013 | Functional/ Integration | Verify Registration link for upcoming events | Homepage loaded | 1. Scroll down to "Events" section 2. Click on Registration link (on each upcoming events) to navigate to Event Details page. 3. Click on Registration | User should be redirected to guild page for the event registration | Critical | No Events are available | Blocked | Data population is not available in the current _data folder. Related historical records exist only in the /archives directory (e.g., _projects, _people). This test case can be exceuted only after migration data is connected to UI.”
TC-CivicTech-014 | Functional | Verify that Venue details are available for the Events | Homepage loaded | 1. Scroll down to "Events" section 2. Click on Registration link (on each upcoming events) to navigate to Event Details page. 3. Click on Location | User should navigate to the venues page. Address and Affiliated Organizations should be available. | High | No Events are available | Blocked | Data population is not available in the current _data folder. Related historical records exist only in the /archives directory (e.g., _projects, _people). This test case can be exceuted only after migration data is connected to UI.”
TC-CivicTech-015 | Functional/ Integration | Verify "Events Registration Page" link | Homepage loaded | 1. Scroll down to "Events" section 2. Click on "Events Registration Page" | User should be redirected to guild page for the events registration | Critical | No Events are available | Blocked | Data population is not available in the current _data folder. Related historical records exist only in the /archives directory (e.g., _projects, _people). This test case can be exceuted only after migration data is connected to UI.”
TC-CivicTech-016 | Functional | Verify "See all Hacknights here" link | Homepage loaded | 1. Scroll down to "Events" section 2. Click on "See all Hacknights here." | User should navigate to Hacknights page. All upcoming and past hacknights should be displayed Registration link should be available for upcoming events. | High | No Events are available | On Hold | Data population is not available in the current _data folder. Related historical records exist only in the /archives directory (e.g., _projects, _people). Test case placed on hold until migration data is connected to UI.”
TC-CivicTech-017 | Functional | Verify "Current Featured Projects" section | Homepage loaded | 1. Scroll down to "Current Featured Projects" section 2. Check projects content | All projects should be listed without layout issues. | Critical | No Projects are available | On Hold | Data population is not available in the current _data folder. Related historical records exist only in the /archives directory (e.g., _projects, _people). Test case placed on hold until migration data is connected to UI.”
TC-CivicTech-018 | Functional | Verify navigation to Project details page | Homepage loaded | 1. Scroll down to "Current Featured Projects" section 2. Click on each project | User should be navigated to Project details page. | Critical | No Projects are available | Blocked | Data population is not available in the current _data folder. Related historical records exist only in the /archives directory (e.g., _projects, _people). This test case can be exceuted only after migration data is connected to UI.”
TC-CivicTech-019 | Functional | Verify Links available on listed Projects | Homepage loaded | 1. Scroll down to "Current Featured Projects" section 2. Click on each link available on the listed projects | Each link should navigates to the correct page without errors. Page content matches its title | High | No Projects are available | Blocked | Data population is not available in the current _data folder. Related historical records exist only in the /archives directory (e.g., _projects, _people). This test case can be exceuted only after migration data is connected to UI.”
TC-CivicTech-020 | Functional | Verify "See all projects" link | Homepage loaded | 1. Scroll down to "Current Featured Projects" section 2. Click on "See all projects here" link | User should be navigated to Projects page. Projects should be listed under 'Current Open Projects' and 'Other Community Projects' | High | No Projects are available | On Hold | Data population is not available in the current _data folder. Related historical records exist only in the /archives directory (e.g., _projects, _people). Test case placed on hold until migration data is connected to UI.”
TC-CivicTech-021 | Functional | Verify "Calls to Action" section on homepage | Homepage loaded | 1. Scroll down to "Current Featured Projects" section 2. Click on each options - About Us, See Resources, Get Involved | Each option should navigate to the correct page without errors. Page content matches its title | High | Each option loads correct page. Content matches with title. | Pass | This test requires a content comparison with the old site.
TC-CivicTech-022 | Functional/ Integration | Verify "Sign Up on Guild" button | Homepage loaded | Click on Sign up on Guild | User should be redirected to https://guild.host/civic-tech-toronto/events Page opens in new tab. | High | User is redirected to desired page in a new tab | Pass
TC-CivicTech-023 | Functional | Verify "See past events" button | Homepage loaded | Click on See past events | User should be navigated to Hacknights page Past Events should be displayed correctly | Medium | No Events are available | On Hold | Data population is not available in the current _data folder. Related historical records exist only in the /archives directory (e.g., _projects, _people). Test case placed on hold until migration data is connected to UI.”
TC-CivicTech-024 | Functional/ Integration | Verify Slack button on the top | Homepage loaded | Click on Slack button on the top right corner | User should be redirected to Slack invite page in new tab. | High | User is redirected to desired page in a new tab | Pass
TC-CivicTech-025 | Functional/ Integration | Verify RSVP button on the top | Homepage loaded | Click on RSVP button on the top right corner | User should be redirected to https://guild.host/civic-tech-toronto/events Page opens in new tab. | High | User is redirected to desired page in a new tab | Pass
TC-CivicTech-026 | Functional | Verify Connect section | Homepage loaded | 1. Scroll down to Connect section. 2. Check options available | Following options should be available - Slack Guild GitHub YouTube Bluesky Instagram LinkedIn | High | All required options are available | Pass
TC-CivicTech-027 | Functional/ Integration | Verify navigation to Slack | Homepage loaded | Click on 'Slack' under Connect | User should be redirected to Slack invite page in new tab. | High | User is redirected to desired page in a new tab | Pass
TC-CivicTech-028 | Functional/ Integration | Verify navigation to Guild | Homepage loaded | Click on 'Guild' under Connect | User should be redirected to https://guild.host/civic-tech-toronto/events Page opens in new tab. | High | User is redirected to desired page in a new tab | Pass
TC-CivicTech-029 | Functional/ Integration | Verify navigation to GitHub | Homepage loaded | Click on 'GitHub' under Connect | CivicTech Toronto GitHub repo should be opened in a new tab | High | User is redirected to desired page in a new tab | Pass
TC-CivicTech-030 | Functional/ Integration | Verify navigation to YouTube | Homepage loaded | Click on 'YouTube' under Connect | YouTube channel should be opened in a new tab | High | User is redirected to desired page in a new tab | Pass
TC-CivicTech-031 | Functional/ Integration | Verify navigation to Bluesky | Homepage loaded | Click on 'Bluesky' under Connect | Bluesky profile should be opened in a new tab | High | User is redirected to desired page in a new tab | Pass
TC-CivicTech-032 | Functional/ Integration | Verify navigation to Instagram | Homepage loaded | Click on 'Instagram' under Connect | Instagram profile should be opened in a new tab | High | User is redirected to desired page in a new tab | Pass
TC-CivicTech-033 | Functional/ Integration | Verify navigation to LinkedIn | Homepage loaded | Click on 'LinkedIn' under Connect | LinkedIn profile should be opened in a new tab | High | User is redirected to desired page in a new tab | Pass
TC-CivicTech-034 | Functional | Verify Change Theme toggle | Homepage loaded | Click on Auto/Light/Dark under Change Theme | Pages should correctly switch themes without layout breakage | Medium | Pages correctly switch theme based on selection | Pass
TC-CivicTech-035 | Functional | Verify Navigation to home by clicking on header logo | Any page on the site loaded | Click on the CivicTech.ca logo in the header. | User should be navigated to the homepage. | Critical | User is navigated to Homepgae | Pass
TC-CivicTech-036 | Functional | Verify Navigation to home by clicking on footer logo | Any page on the site loaded | 1. Scroll to the footer of the page 2. Click on the CivicTech.ca logo | User should be navigated to the homepage. | High | User is navigated to Homepgae | Pass
TC-CivicTech-037 | Functional | Verify that back button on browser navigates correctly | User has navigated between multiple pages | 1. Click the browser's back button 2. Click the browser's forward button | User should be correctly navigated back to the previous page and forward to the next page in the history. | Critical | User is correctly navigated back and forward based on actions | Pass
TC-CivicTech-038 | Functional/ Integration | Verify that email feature works properly | Get Involved page is loaded | Locate and click on the "hi@civictech.ca" email link | User's default email client should opens | High | Email options are opened to the user | Pass
TC-CivicTech-039 | Functional/ Integration | Verify that "Get Involved" links work correctly | About Us page is loaded | 1. Scroll down to the "Get Involved" section 2. Click on the "Sign Up" link 3. Click on the "Email Us" link 4. Click on the "Get In Touch" link | All links should navigate to the correct external pages or open the email client as expected. | High | Each link correctly navigates to desired page. | Pass
TC-CivicTech-040 | Functional/ Integration | Verify that Events registration link on Hacknights page works correctly | Hacknights page is loaded | Click on the "Events Registration" link | User should navigated to the correct external event registration page | High | User is navigated to guild hacknights page | Pass
TC-CivicTech-041 | UI/UX | Verify Responsive layout | Website is running locally (http://localhost:4000) | Resize window/mobile view | Layout should be adjusted correctly | Critical | Minor UI (text aligment) issue in homepahe | Fail
TC-CivicTech-042 | UI/UX | Verify consistency of fonts & colours | Website is running locally (http://localhost:4000) | Check across pages | All pages should follow consistent design | Low | All pages follow consistent design | Pass
TC-CivicTech-043 | UI/UX | Validate dark mode readability | Website is running locally (http://localhost:4000) | Switch to Dark mode | Text and UI elements should be visible | Medium | Text and UI elements are visible | Pass
TC-CivicTech-044 | Accessibility | Verify accessibility (WCAG 2.1 AA) | Website is running locally (http://localhost:4000), Browser with accessibility tools | 1. Run WAVE/axe scan 2. Navigate site | No major WCAG violations | High | No major WCAG violations | Pass
TC-CivicTech-045 | Accessibility | Verify readability of content | Website is running locally (http://localhost:4000) | Review text contrast, fonts, spacing across pages | Content should be clear and legible | Medium | Content is clear and legible | Pass
TC-CivicTech-046 | Accessibility | Verify alt text for images | Website is running locally (http://localhost:4000) | Inspect image tags | All images should have descriptive alt text | High | Image has alt text and readable on NVDA speech viewer | Pass
TC-CivicTech-047 | Accessibility | Verify colour contrast | Website is running locally (http://localhost:4000) | Check text/background contrast | Contrast ratio should meet WCAG AA | High | Few colour contrast issues observed in homepage using CCA (colour contrast analyzer) | Fail
TC-CivicTech-048 | Accessibility | Verify logical heading structure | Website is running locally (http://localhost:4000) | Use a screen reader/ NVDA to view the page's heading hierarchy. | The page should have a single <h1> tag. Subsequent headings (<h2>, <h3>, etc.) follow a logical, descending order without skipping levels. | Critical | Heading structure is correct | Pass
TC-CivicTech-049 | Accessibility | Verify skip-to-content link | Website is running locally (http://localhost:4000) | On any page, press the Tab key immediately after loading. | A "Skip to main content" link should appear at the top of the page. Clicking it moves the focus to the main content area, bypassing the navigation. | Critical | Skip to main content appears and on clicking it navigates to main landmark | Pass
TC-CivicTech-050 | Accessibility | Verify keyboard navigation | Website is running locally (http://localhost:4000) | Navigate with tab key | All elements should be accessible via keyboard | High | All elements are accessible with keyboard | Pass
TC-CivicTech-051 | Accessibility | Verify all interactive elements are keyboard focusable and in logical order | Website is running locally (http://localhost:4000) | Use the Tab key to move through the page's interactive elements. | All interactive elements (links, buttons, etc) should receive keyboard focus in a logical order. The focus should be visible and clear (never trapped) | Critical | The focus is clear on each element and in logical order. | Pass
TC-CivicTech-052 | Accessibility | Verify link purpose is clear from context | Website is running locally (http://localhost:4000) | 1. Identify all links on the page. 2. Read the link text. | The link text should clearly describe the destination, or its purpose should be clear from the surrounding paragraph | Critical | Link texts are correctly described | Pass
TC-CivicTech-053 | Migration | Verify Gem dependencies | Bundle installed | 1. Run bundle install 2. Observe dependency installation | All gems should install successfully, no conflicts | Critical | Installation successful. No conflicts observed | Pass
TC-CivicTech-054 | Migration | Verify Jekyll Build Runs Successfully | Ruby, Bundler, and Jekyll installed. Repo cloned. | 1. Open terminal, navigate to project root. 2. Run bundle exec jekyll build. | Build completes with no errors, _site folder generated with static HTML pages. | Critical | Site successfully runs locally | Pass
TC-CivicTech-055 | Migration | Verify All Data Files Included | Repository cloned. | 1. Open _data/ folder (contains YAML/CSV). 2. Confirm if config files exist: categories.yml, tags.yml, navigation.yml, footer_social.yml, social_links.yml 3. Open a few sample files and verify valid YAML frontmatter is present. 4. Verify if following data files exists: projects/, _people/, _resources/, _venues/, _hacknights/. | All content sources should be available and linked to UI pages. | Critical | All required .yml collections are available under data folder. However the following data files are available under archives: _projects/, _people/, _resources/, _venues/, _hacknights/. | Fail | Expected data files (e.g., _projects, _people) to be present in active collections and linked to UI. Currently, these files exist only under /archive/ directory and are not surfaced on the live site. Require clarification on whether archived data will be migrated into live collections.
TC-CivicTech-056 | Migration | Validate Archived Events Migration | Archive data available in _data/archives.yml or equivalent. | 1. Navigate to /archives/. 2. Cross-check dates, titles, and links with _data/archives.yml (if exists). | Historical content should be present and structured correctly. | High | Required content is present and structured correctly. | Pass
TC-CivicTech-057 | Migration | Validate Archived Data Rendering | Local server running via bundle exec jekyll serve. | 1. Open browser → go to relevant entity pages (e.g., /[entity]). 2. Verify if records appear. 3. If empty, check that placeholder page still loads with header + navigation. | Menus/pages exist but may show empty records (expected until wiring done). Pages do not break. | Critical | Pages are opened correctly with headers. | Pass
TC-CivicTech-058 | Migration | Validate data integrity | Local server running | 1. Open _data/*.yml file (e.g., projects.yml). 2. Pick one record (e.g., project title + URL). 3. Open browser → Navigate to /list-projects/. 4. Cross-verify the displayed content matches YAML data. | All records migrated correctly | Critical | Displayed content matches data. | Pass
TC-CivicTech-059 | Security | Verify HTTPS redirection | Local server is running | Enter http://civictech.ca | Should auto-redirect to HTTPS | Critical | Local environment runs only on http://localhost:4000. HTTPS redirection can only be validated on the deployed production site. | N/A | Test deferred until deployment to hosting environment with SSL enabled.
TC-CivicTech-060 | Security | Verify Security HTTP Headers | Local server is running | 1. Open browser DevTools (F12). 2. Go to Network tab. 3. Refresh the site (Ctrl+R). 4. Click on the root document request (/ or index.html). 5. Inspect Response Headers. | Ensure presence of key security headers: Content-Security-Policy Strict-Transport-Security X-Frame-Options X-Content-Type-Options Referrer-Policy Permissions-Policy | Medium | Only basic headers observed (Cache-Control, Connection, etc.). No security headers found, which is expected since the site is running on localhost using WEBrick (Ruby server). | Blocked | Cannot validate fully in local. Note: This is the expected behavior for GitHub Pages hosting, as custom security headers are not automatically included. If stronger security is required, headers must be added via a proxy/CDN configuration
TC-CivicTech-061 | Security | Verify Broken Links / External Redirects Security | Local server is running | 1. Open command prompt/terminal. 2. Install broken-link checker tool (one-time): npm install -g broken-link-checker 3. Run link check against local site: blc http://127.0.0.1:4000 -ro 4. Review output for broken/malicious links. | No broken internal links. All external links resolve correctly (Slack, Guild, YouTube, etc.). No redirects to suspicious domains. | High | Broken Link Checker reports the Bluesky external profile link as broken. Manual verification confirms the link is valid and opens correctly in a browser. | Pass | False positive due to automated crawler restrictions. External link is functional.
TC-CivicTech-062 | Compatibility | Verify Chrome compatibility | Chrome browser | Open site in Chrome | Site should work properly | Critical | Site works properly | Pass
TC-CivicTech-063 | Compatibility | Verify Firefox compatibility | Firefox browser | Open site in Firefox | Site should work properly | High | Site works properly | Pass
TC-CivicTech-064 | Compatibility | Verify Edge compatibility | Edge browser | Open site in Edge | Site should work properly | High | Site works properly | Pass

## Execution_Performance
Test Case ID | Type | Test Title | Test Steps | Test Data/Load | Expected Results | Priority | Actual Result | Status | Avg Response Time (ms) | 90th Percentile (ms) | Error % | Notes/ Remarks
TC-CivicTech-065 | Performance | Verify homepage load time | Measure load time on homepage | 1 user, 10 iterations | Page should load within 3 seconds | High | Homepage loaded successfully every time | Pass | 25 | 31 | 0 | Page currently does not contain events and projects data. Functional issue raised – response time may not reflect real usage
TC-CivicTech-066 | Performance | Verify Get Involved page load time | Measure load time on Get Involved page | 1 user, 10 iterations | Page should load within 3 seconds | Medium | Page loaded successfully | Pass | 56 | 66 | 0
TC-CivicTech-067 | Performance | Verify Hacknights page load time | Measure load time on Hacknights page | 1 user, 10 iterations | Page should load within 3 seconds | High | Page loaded successfully | Pass | 56 | 64 | 0 | Page currently does not contain data. Functional issue raised – response time may not reflect real usage
TC-CivicTech-068 | Performance | Verify Projects page load time | Measure load time on Projects page | 1 user, 10 iterations | Page should load within 3 seconds | High | Page loaded successfully | Pass | 58 | 64 | 0 | Page currently does not contain data. Functional issue raised – response time may not reflect real usage
TC-CivicTech-069 | Performance | Verify Resources page load time | Measure load time on Resources page | 1 user, 10 iterations | Page should load within 3 seconds | Medium | Page loaded successfully | Pass | 56 | 64 | 0 | Page currently does not contain data. Functional issue raised – response time may not reflect real usage
TC-CivicTech-070 | Performance | Verify stress load on Home page | Simulate 50+ users navigating homepage | 100 users, 60 iterations, 300 seconds | Home page should remain stable | High | The site handles up to 50 concurrent users very well. At 100 users, homepage response time increases significantly, but no errors occurred. | Pass | 728 | 951 | 0 | Homepage performed well, but note: it currently has no events/projects data → results will likely change once real data/content is added.
TC-CivicTech-071 | Performance | Verify stress load on Events page | Simulate 50+ users navigating events | 100 users, 60 iterations, 300 seconds | Events/Hacknights page should remain stable | High | The site handles up to 50 concurrent users very well. At 100 users, homepage response time increases significantly, but no errors occurred. | Pass | 219 | 273 | 0 | Events page performed well, but note: it currently has no data → results will likely change once real data/content is added.
TC-CivicTech-072 | Performance | Verify caching/performance of static assets (Image, CSS, JS) | Check if static assets (CSS, JS, Image) load fast and consistently under concurrent users in Jmeter. i) Add 3 separate HTTP Request Samplers. ii) Add Response (200) and size (>0) assertions to each sampler. iii) Run | 50 users, 20 iterations, 2 loops HTTP Request Samplers: Sampler 1: /assets/style.css Sampler 2: /assets/modal.js Sampler 3: /images/<your-image-name>.png | Assets should load quickly (<1s) with 0% errors. | Medium | All assets loaded with average <30 ms; no errors. | Pass | 22 | 32 | 0

## Results - Stress Load
Round | Users | Avg Resp (Homepage) | Avg Resp (Events) | 90th Percentile | Errors % | Throughput (Total) | Result
1 (Light) | 10 | 49 ms | 61 ms | <80 ms | 0% | 164/sec | Pass
2 (Moderate) | 50 | 282 ms | 222 ms | ~350 ms | 0% | 185/sec | Pass
3 (Heavy) | 100 | 728 ms | 219 ms | ~950 ms (Home) | 0% | 187/sec | Pass (with degradation)
Conclusion
The site handles up to 50 concurrent users very well (sub-second response times).
At 100 users, homepage response time increases significantly, but no errors occurred.
Events page performed well, but note: it currently has no data → results will likely change once real data/content is added.
Notes / Limitations
Performance testing was executed on the local Jekyll development server (bundle exec jekyll serve).
Response times are significantly faster than production since the server is static and runs on localhost.
Results are valid only for script validation and relative comparison of pages, not for benchmarking real-world performance.
Events, Projects, and Resources pages/sections currently do not contain data. While performance results show low response times, these are not reflective of actual user experience once data is populated. A functional issue has been logged for the missing data.